## bugs
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce | Notes
1 | 2024-02-13 | Jubelle | P0 | open | Justin | Sometimes player sprite will fly off the edge while still pressing an arrow key (will reappear on release) | sprite should always visually stop at edge | sprite sometimes does not visually stop (but will go back to edge posn after key release) | not entirely sure, but it sometimes happens if you hold down an arrow key and let it move out of the game window bounds
2 | 2024-02-11 | Trevor | P1 | resolved | Trevor | Coding bug but C++ wasn't finding the declaration of. Ability in the character class. |  |  |  | I had to reword the Turn Counter Vector to use pointers instead of just the Turn Counter objects themselves
3 | 2024-02-12 | Trevor | P1 | resolved | Trevor | Turn Counter was being constructed correctly but later on when referenced the placement speed values were garbage values no where remotely correct. I had to reword the Turn Counter Vector to use pointers instead of just the Turn Counter objects themselves |  |  |  | I had to reword the Turn Counter Vector to use pointers instead of just the Turn Counter objects themselves
4 | 2024-02-12 | Trevor | P1 | resolved | Jubelle | Attacking when it's a characters Turn was dealing zero damage. |  |  |  | After debugging realized I only called our process action method when the character was an enemy and forgotten to call add an else case
5 | 2024-02-16 | Justin | P1 | resolved | Hans | nullptr exception when spamming the x button on the 'added_rng_miss_chance' branch | game should not crash | game crashes | repeatedly press x button on the combat scene
6 | 2024-02-16 | Justin | P2 | open | Deo | Damage will occasionally spike to huge values for no reason | damage should stay consistent | damage is inconsistent | keep attacking and you will see the random spike in value
7 | 2024-02-16 | Justin | P1 | resolved | Ameya | Game crashes if enemy is attacked after a specific restart | game should not crash | game crashes | restart game using R-key in the combat scene and then hit an enemy | Assertion failed: has(e) && "Entity not contained in ECS registry", file C:\Users\justi\Documents\GitHub\team3-BaristaBeatBattle\template\src\tiny_ecs.hpp, line 78
8 | 2024-03-03 | Trevor | P3 | resolved | Trevor | The characters were taking twice as much damage. | Character should take normal damage | Character takes twice damage | Fix: Turned out when I was doing the dealDamage(dmg) method I was subtracting what would be the damage from the current health points instead of setting it to the new value. I computed what the new value should be because I didn't want character to get below 0 hp but was subtracting instead of setting it outright
9 | 2024-03-03 | Justin | P2 | resolved | Hans | Pressing R makes many things break on M2_Submission branch | Pressing R should reset game as normal | Will send back to overworld but also make it so engaging with an enemy crashes the game | Press R will send us back to the overworld but it will also make it so that engaging with an enemy crashes the game
10 | 2024-03-02 | Justin | P1 | open | Justin | Bug for combat where it crashes when you try to do combat again | Should be able to go into combat multiple times | Cannot go through combat a second time | go through combat once and try to run into a new enemy
11 | 2024-03-05 | Trevor | P3 | resolved | Ameya | Audio doesn't cut off when turnbased ends | Minigame music cuts off | Minigame music doesnt cut off | End the minigame
12 | 2024-03-05 | Jubelle | P3 | resolved | Jubelle | Player mesh does not scale right | User can see whole sprite | User sees a squised sprite
13 | 2024-03-05 | Jubelle | P1 | open | All | When trying to build the file, project path sometimes fails to boot | Game boots | Game fails to boot | Is Random | The only fix we have found is commenting back in and out project_path.hpp or running a clean build
14 | 2024-03-05 | Deo | P0 | resolved | Deo | pressing D on the overworld craches the game | it should show debug lines for collision detection | game crashes | press D on the minigame
15 | 2024-03-26 | Trevor | p4 | resolved | trevor | rest deals damage to character instead of healing | heals character | deals damage to character | use the rest funciton in the turn based
16 | 2024-03-26 | Jubelle | p1 | resolved | hans | minigame never ends, also doesn't render | minigame should render and end after a while | minigame never ends, also doesn't render | enter the mingame stage
17 | 2024-03-26 | Jubelle | p3 | resolved | Jubelle | health bars not rendering | health bars should render in combat mode | health bars not rendering | enter combat mode
18 | 2024-03-26 | Hans | p2 | resolved | hans | Going back to main menu manually by pressing "M", causes some weird animations to occur | Going back to main menu manually should not cause any errors | Going back to main menu manually by pressing "M", then stepping through to turn-based causes some weird animations to occur | go to the main menu using 'm' and then step through the turn based mode
19 | 2024-03-26 | Justin | p4 | resolved | Justin | velocity update (for nicer visual transition between levels) does not work. | transition between levels should look smooth | level transition is very rough | overworld_system doesn't handle game loop, so velocity update (for nicer visual transition between levels) does not work. | move create_overworld_levels function, into the overworld system for M4
20 | 2024-03-26 | Ameya | p4 | resolved | Ameya | cutscene shifts back and forth depending on players last movment | cutscene should stay stagnent | cutscene shifts back and forth depending on players last movment | collide with an enemy while moving | when the player goes into the cutscene the background will go slightly to the left or right depending on the way the player was last moving, resolved by changing texture idea
21 | 2024-03-26 | Ameya | p2 | open | Trevor | going into new level after first level causes strange animations | going into a new level should render and play fine just like the first level | going into new level after first level causes strange animations | finish one level and enter into the next level and start attacking the enemy
22 | 2024-03-27 | Justin | p1 | open | Justin | restarting game causes custcenes not to render | restarting the game should allow player to start new game an go through levels properly | levels do not render the player, enemies, or anything else | Pressing R to reset doesn't properly reset the game, it makes it so that levels do not render
23 | 2024-03-27 | hans | p3 | resolved | Trevor | Party members that aren't chai do not have minigame ability | all members should be able to use the minigame ability | Party members that aren't chai do not have minigame ability | Go to level 3, play minigame with a party member that's not chai, and a nullptr value will be thrown, as the ability being referenced has no power. | for some reason, this also affects the positioning of the cup in the minigame.

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release