## bugs
Bug List
# | Reported Date | Reported By | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce | Notes
1 | 2024-02-13 | Jubelle | P0 | open | Justin | Sometimes player sprite will fly off the edge while still pressing an arrow key (will reappear on release) | sprite should always visually stop at edge | sprite sometimes does not visually stop (but will go back to edge posn after key release) | not entirely sure, but it sometimes happens if you hold down an arrow key and let it move out of the game window bounds
2 | 2024-02-11 | Trevor | P1 | resolved | Trevor | Coding bug but C++ wasn't finding the declaration of. Ability in the character class. |  |  |  | I had to reword the Turn Counter Vector to use pointers instead of just the Turn Counter objects themselves
3 | 2024-02-12 | Trevor | P1 | resolved | Trevor | Turn Counter was being constructed correctly but later on when referenced the placement speed values were garbage values no where remotely correct. I had to reword the Turn Counter Vector to use pointers instead of just the Turn Counter objects themselves |  |  |  | I had to reword the Turn Counter Vector to use pointers instead of just the Turn Counter objects themselves
4 | 2024-02-12 | Trevor | P1 | resolved | Jubelle | Attacking when it's a characters Turn was dealing zero damage. |  |  |  | After debugging realized I only called our process action method when the character was an enemy and forgotten to call add an else case
5 | 2024-02-16 | Justin | P1 | resolved | Hans | nullptr exception when spamming the x button on the 'added_rng_miss_chance' branch | game should not crash | game crashes | repeatedly press x button on the combat scene
6 | 2024-02-16 | Justin | P2 | open | Deo | Damage will occasionally spike to huge values for no reason | damage should stay consistent | damage is inconsistent | keep attacking and you will see the random spike in value
7 | 2024-02-16 | Justin | P1 | open | Ameya | Game crashes if enemy is attacked after a specific restart | game should not crash | game crashes | restart game using R-key in the combat scene and then hit an enemy | Assertion failed: has(e) && "Entity not contained in ECS registry", file C:\Users\justi\Documents\GitHub\team3-BaristaBeatBattle\template\src\tiny_ecs.hpp, line 78
8 | 2024-03-03 | Trevor | P3 | resolved | Trevor | The characters were taking twice as much damage. | Character should take normal damage | Character takes twice damage | Fix: Turned out when I was doing the dealDamage(dmg) method I was subtracting what would be the damage from the current health points instead of setting it to the new value. I computed what the new value should be because I didn't want character to get below 0 hp but was subtracting instead of setting it outright
9 | 2024-03-03 | Justin | P2 | open | Hans | Pressing R makes many things break on M2_Submission branch | Pressing R should reset game as normal | Will send back to overworld but also make it so engaging with an enemy crashes the game | Press R will send us back to the overworld but it will also make it so that engaging with an enemy crashes the game
10 | 2024-03-02 | Justin | P1 | open | Justin | Bug for combat where it crashes when you try to do combat again | Should be able to go into combat multiple times | Cannot go through combat a second time | go through combat once and try to run into a new enemy
11 | 2024-03-05 | Trevor | P3 | open | Ameya | Audio doesn't cut off when turnbased ends | Minigame music cuts off | Minigame music doesnt cut off | End the minigame
12 | 2024-03-05 | Jubelle | P3 | open | Jubelle | Player mesh does not scale right | User can see whole sprite | User sees a squised sprite
13 | 2024-03-05 | Jubelle | P1 | open | All | When trying to build the file, project path sometimes fails to boot | Game boots | Game fails to boot | Is Random | The only fix we have found is commenting back in and out project_path.hpp or running a clean build

## bug_severities
Severity | Description
P0 | crash bug; game crashes and is unrecoverable
P1 | game stopping bug, but no crash; cannot keep playing
P2 | serious, game not working as expected
P3 | annoying, could ship but loss of marks
P4 | annoying or limiting, but could be shipped as-is
P5 | minor or feature that nice to have but could ship in future release